## Sheet1
Project | Purpose | Output | Timing | Responsible | Comments | September Update | October | November | December
General Admin
ToRs | Outline function / arrangements / responsibilities of WASH WG | Updated document | September | David / Zaid |  | Initial draft seemingly rejected by UNICEF in favour of NGO forum draft. Revised draft ongoing before sharing with partners
Strat. Op. Framework | Outline min. activities / targets of WASH Sector as common basis for actors and reference for donors | SOF | September | David / Zaid |  | Consultations to date have now provided sufficient substance for revised initial draft
Meetings / Minutes | For coordination / technical exchanges / updates | Meetings / Minutes | Bi-weekly | David |  | Establishment in Gaziantep / Antakya. Ongoing
Contact List | Facilitate communications between WASH partners | Up to date contact list | Monthly | David |  | Established. Need to formalise for monthly updates
Calendar | Facilitate participation of other actors | CoCal updated | Bi-weekly | David |  | Inputs provided regularly to NGO Forum / OCHA
Document Repository | Facilitate sharing of key documents / outputs | Repository established | Ongoing | David |  | Google groups / website options evaluated and rejected. Dropbox established
Data protocol | TBD | TBD | TBD | David |  | Being drafted in CCCM - to be seen if needed for WASH given current data flows
Technical Working Groups |  |  |  | David
Leishmaniasis | Tech guidance on vector control | Guidance Note | October |  |  | Ongoing with Mentor Initiative (lead)
Hygiene Promotion | Common IEC materials | Tested IEC materials | Ongoing |  |  | Ongoing with MRFS (lead), WVI, SCI, MSFF
Hygiene Kits | Common content / targetting criteria | Guidance note on minimums | October |  |  | Ongoing with Gaziantep WG / NFI WG
Medical Waste / WASH | Common approach | Guidance Note | November |  |  | To be initiated with arrival of dedicated resource in MRFS, and with MSFs
Solid Waste | Common approach | Guidance Note | October |  |  | Initiated amongst PIN, MRFS, SCI, MC
Water testing facilities | For specific quality needs | Contact lists | September |  |  | Researched and provided. Ongoing
Chlorine transport / suppliers | For provision within Syria | Contact lists | September |  |  | Researched and provided. Ongoing
Inter-Sectoral Working Group |  |  |  | David/Zaid
ToRs | Outline function / arrangements / responsibilities of ISCG | Finalised document | September |  |  | Redrafted & circulated, discussed with OCHA, finalised with ISCG
Targetting Criteria | Harmonisation with FSLWG / NFIs | Harmonised guidance | October |  |  | To be initiated in next meeting
Contingency planning | Preparedness | Updated document | Ongoing |  |  | Inputs provided. On standby
Information Management
Indicators | Basis for sectoral reporting | Response Indicators | September | Zaid |  | Zaid now lead on this
3Ws | Tool for sectoral reporting / coordination | Updated format | September | STIMA / David |  | To be built on agreed indicators / products & existing data flows
SitReps | Overview of gaps / needs | Monthly document | October | OCHA / David |  | Need to work closer with OCHA to ensure their picture is correct and provide inputs for WASH specific SitRep
Updates | Overview of ongoing activities / key issues | Updates | Bi-weekly | David |  | Provided at NGO Forum / HCM. Ongoing
Contingency stocks | Overview of spare capacities | Updated document | Monthly | David |  | Format established / circulated. Need to formalise for monthly updates
Needs Assessments |  |  |  | David/Zaid
Assessment Repository |  |  | Ongoing | STIMA |  | Format agreed. To be rolled out
Inter-sectoral Assessments |  |  | Ongoing | STIMA |  | To be pushed forward to extent possible in the coming meetings and raised in ISCG
E-WARN |  |  | Ongoing | ACU |  | Contacts established. Technical inputs to be provided where possible
DYNAMO |  |  | Ongoing | ACU |  | Contacts established. Technical inputs to be provided October