## Coord. Transition Strategy
Core Coordination Functions Matrix
Core cluster function | Definitions | Comments | Benchmark for oPt | Benchmark (for gov. take over of cluster functions) currently met? | Responsible agency 2015 | Responsible agency post 2015 | Resources required from UNICEF post 2015
Supporting service delivery | Providing a platform that ensures service delivery is driven by the Strategic Response Plan and strategic priorities. | Water Development platform & humanitarian platform should be linked | Resourced PWA/EWASH platform in place and providing active guidance to the coordinator | No | UNICEF / PWA / PHG | PWA / [EWASH] | GWC Coordination support as needed UNICEF Programme support
| Developing mechanisms to eliminate duplication of service delivery. | See IM Strategy | IM system in place between humanitarian and development actors | Partial | UNICEF / PWA / [PHG] | PWA / [EWASH] | GWC IM support
Informing strategic decision-making of the HC/HCT for the humanitarian response | Preparing needs assessments and analysis of gaps (across and within sectors, using information management tools as needed). | 2 aspects: - comprehensive WASH monitoring system - harmonised assessment for shocks | WASH Monitoring system reestablished | No | PHG UNICEF / [EWASH] | PWA / [EWASH] | GWC Assessment support
| Identifying and finding solutions for (emerging) gaps, obstacles, duplication and cross-cutting issues. | Requires integrated development / humanitarian solutions | Formal links between development / humanitarian platforms | No | UNICEF / PWA / [EWASH] | PWA / [EWASH] | UNICEF Programme support as needed
| Formulating priorities on the basis of analysis |  |  | Partial
Planning and strategy development | Developing sectoral plans, objectives and indicators that directly support realization of the response’s strategic priorities. | Refers to both the SRP but also other thematic response plans | PWA / EWASH develop own sectoral strategic operating framework and plans | Partial | UNICEF / PWA / [EWASH] | TBD | UNICEF Programme support as needed
| Applying and adhering to common standards and guidelines. | In addition to PWA defined standards, standards defined in the WGs (and incorporated into the SOF) | PWA / EWASH promote standards and engage in quality assurance to ensure standards are met | No | UNICEF / PWA / [EWASH] | TBD
| Clarifying funding requirements, helping to set priorities, and agreeing cluster contributions to the HC’s overall humanitarian funding proposals. | Requires formal links to the IASC structures | PWA / EWASH identifies funding requirements for humanitarian activities, and utlilizes mechanisms to seek funds through humanitarian or development channels | Partial | UNICEF / PWA / [EWASH] | TBD | UNICEF Programme support as needed
Advocacy | Identifying concerns that contribute to HC and HCT messaging and action. | Requires formalisation of EWASH ATF as representing the WASH Sector | PWA / EWASH able to articulate and broadly communicate (with results) its key concerns within the WASH sector | Partial | UNICEF / PWA / [EWASH] | PWA / [EWASH]
| Undertaking advocacy on behalf of the cluster, cluster members, and affected people. |  |  |  | UNICEF / PWA / [EWASH] | PWA / [EWASH ATF]
Monitoring and reporting | Monitoring and reporting on activities and needs. Measuring performance against the cluster strategy and agreed results. Recommending corrective action where necessary. | Dependent on IM Strategy | PWA / EWASH integrates humanitarian and development actors within the same monitoring matrix PWA / EWASH analyzes results and develops action plan when targets are not met | No | UNICEF / PWA / [EWASH] | PWA / [EWASH ATF] | UNICEF Programme support as needed
Contingency/preparedness planning |  |  | PWA / EWASH develops comprehensive contingency and preparedness plans for the WASH sector (national, governorate and potentially municipal) | No
Acountability to Affected Population
Criteria for de-activation | Definition |  | Benchmark for oPt | Benchmark (for deactivation) met? | Responsible agency 2015 | Responsible agency post 2015 | Resources required from UNICEF post 2015
Transition of responsibility | The cluster has transferred responsibility for delivery and possibly capacities, tools, systems and resources to national and/or development partners | Requires ensuring the above points such that the core coordination functions are ensured | More than 75% of the core coordination functions are taken on by PWA / EWASH | No
Decrease in need | Humanitarian needs in a particular sector have sharply decreased or ceased (e.g. when affected people have returned, reintegrated or relocated) | Requires ensuring the above points such that government / development partners can deal with the chronic crisis. | Key stakeholders agree that humanitarian need (or reasonable risk of recurrence) in all or part of the oPt has decreased to the point where the government and development partners can manage any residual emergency WASH activity | No
Requirements for longer transition | Definition |  | Benchmark for oPt | Benchmark (for longer transition) met? | Responsible agency 2015 | Responsible agency post 2015 | Resources required from SC/UNICEF post 2015
Continued need | Continuing requirement to address critical humanitarian needs and the violation of human rights | We need to ensure that WASH demolitions are addressed And to ensure that strong monitoring exists that can feed IHL/IHRL monitoring & advocacy | Decreased need OR existing government / development capacity to address | Yes
Accountabilities | Need to maintain accountability for delivery in key sectors | UNICEF is obliged to retain overall accountability until can deactivate. However, through the SAG UNICEF will do this while simultaneously sharing accountability with the PWA/EWASH |  | Yes
National counterparts | Existence, capacity and willingness of national counterparts to lead sectoral coordination | The PWA does not yet have the dedicated resources / structure to take over fully | PWA / EWASH has dedicated capacity and appropriate structures | Yes
Recurrence | Possibility of recurring or new disasters | The likelihood of a return to hostilities in Gaza remains, with additional risk of seasonal natural disasters |  | Yes

## IM Strategy
WASH Sector IM Strategy - oPT - comments to dalford@unicef.org | [12 empty] | Updates
ID | Information Management Project | Tools (in GWC IM toolkit) | Purpose | Output | Method | Timing | Disseminate to | HRs Required: 2015 UNICEF 2016 [PWA/ EWASH] | Responsible to Implement | Initial Work | Future Work Needed | Notes
A. ADMINISTRATION
1 | WASH IM Strategy (this document) | n/a | Priortise actions for IM response to Typhoon Pablo | IM Strategy | Developed on spreadsheet | Updated when required | n/a | IMO | IMO | Written but under-resourced to follow | Recruitment / training of IMOs | This is a working document
2 | WASH Cluster Contact list | Admin tools | To send information such as population statistics, SitReps, meeting information, 3W matrices, etc. to pre-defined groups; to share a centralised master repository of email addresses | Contact List | Developed on spreadsheet | Updated with new staff/sector members and uploaded | n/a | IMO | IMO | Currently excel / google excel based | Establish MailChimp app on webpage for self sign-up and sign-out | While excel based important that a single focal point responsible for updating for Gaza and West Bank
3 | WASH meeting calendar | Admin tools | Keep list of meetings | Online calendar | HR.info | Ongoing | n/a | IMO | IMO / EWASH ATF | Currently using HR.info calendar | Establish single WASH Calendar (EWASH / WDWG / Cluster) on future website | While using HR.info Sector IMO must coordinate with PWA / EWASH to update meetings
4 | Document repository (for working documents/ not for public) | n/a | Keep online repository for WCCs/IMOs to exchange documents | Online folder | Dropbox | Ongoing | WCCs/IMOs | IMO | IMO | Dropbox based | Files need to be cleaned up!!
5 | Back up system | n/a | Save data! | UNICEF WASH Drive | Weekly backup of dropbox | Ongoing | n/a | IMO | WCC/IMO
B. DATA & INFORMATION
6 | Assessment & Information Management Working Group | n/a | Chaired by OCHA - Aims to coordinate inter-sector information activities - including needs assessments and monitoring systems - between information management specialists; also, to be a forum for disseminating information to the interagency community | Joint information management activities; harmonised datasets and other cross-sectoral information along with information on assessments |  | Monthly? Ad hoc? Unclear… | n/a | IMOs | IMO | Inter-sectoral cross-table shared with OCHA | This needs to be insisted on - we depend on info from other Sectors that is not currently available. In addition basic shapefiles are not on the CODs | Currently more or less ineffectual
7 | Base and Ancillory Spatial Data Collation / Audit | n/a | To gather existing datasets to cross analyse | Used in GIS | Via AIM WG / PWA / CMWU (and other sources e.g. other Cluster IMOs) gather all relevant datasets, and establish links to obtain / update data on regular basis | Ongoing | n/a | IMOs | IMO | Review of existing datasets. Took time to develop trust / gain access. | Integrate IM within CMWU / PWA. Work cross Clusters e.g. Shelter & Health ASAP
C. ASSESSMENT
8 | Needs Assessment Inventory / Metadata | Excel template | Create or augment OCHA inventory (and feed back to them for portal upload) the needs assessments/metadata for assessments to maximise the use of commonly available information and to avoid over-assessment | Excel or PDF, share to agencies and partners | Ask partners for all assessments; check operational website for other cluster assessments that might be of interest; add information to metadata template; upload assessments to operational website; inform partners that the assessments exist | Continuous | Share filled template to Partners and OCHA | Partners, CC, IMO | IMO | Excel circulated during HNO development | Needs to be recirculated / readdressed to ensure sharing of findings and coordination of coverage
9 | Qualitative Data Analysis | A User Manual on how to use QDA Miner for WASH Sector assessment analysis -This is a KEY task for the IMO | To analyse and consolidate all assessments that are shared with the Cluster from Word to PDF to satellite imagery etc. and share in a thematic and geographic way back to partners | Numerous incl. Excel, Word, PDF, Google Earth KMLs. | Follow the step-by-step manual on how to complete an analysis of the assessments. Ensure that the results are widely shared to all interested parties. | Mostly at start of emergency (M1-2) or when funding rounds occur and assessments are required to back up proposals | Share analysed assessments to Partners and OCHA | Partners, CC, IMO, OCHA | IMO | n/a | Requires further work in terms of data audit across relevant actors / sectors
10 | WASH Needs Assessment harmonised methodologies | Indicators, Question Bank, Mobile Device Software, Assessment Templates | To assist partners in the choosing of indicators, questions and software to carryout assessments, includes partner examples | Harmonised methodology | Ensure partners know of the existence of the tools. Discuss using core indicators and questions with partners to harmonise assessments. Enquire about the expertise of partners with regard to carrying out assessments with mobile devices and share contacts on expertise to other partners | Mostly at start of emergency (M1-2) or when funding rounds occur and assessments are required to back up proposals | Share directly to partners a few times during emergencies as a reminder | IMO | IMO | n/a | IMO to collect existing forms/info from partners and propose method. | 1. For displacement 2. For conflict 3. For demolitions (exists but may need improvement)
C. NEEDS & CASELOAD
11 | Demolitions (West Bank) | n/a | To track demolitions, WASH needs assessments and WASH responses | Inputs to demolitions tracker |  |  |  | IMO | ECHO Consortium / IMO | n/a - new online system developed and do not have access to old or new. | Ensuring clear data flows, but also a clear reference system outside of the Consortium | Demolitions tracker system managed by OCHA
12 | Water Monitoring (West Bank) | n/a | To provide an overall picture of water scarcity in the West Bank for sector-wide programming / advocacy / fundraising purposes | Data - freely accessible by WASH actors and EWASH ATF | Using the indicators defined in 2012 | Annual |  | IMOs | PHG / GVC | Top Priority' SRP Project by PHG / GVC introduced on this specifically | Close work with PHG / GVC to ensure databases linked to ActivityInfo (in collaboration with PWA) | With no comprehensive data very difficult to sell WASH
13 | Flood Risk Mapping (Gaza Strip) | n/a | To highlight high flood risk areas in Gaza Strip | Data - freely accessible by WASH actors and EWASH ATF | ACF conducted for southern Governorates in 2014, SRP 2015 project for northern Governorates | Annual |  | IMO | ACF | Facilitated access to key datasets to ACF, and encouraged 'top priorty' SRP project | Ensure that the Data is freely accessible and linked to ActivityInfo (in collaboration with CMWU / PWA)
14 | WASH Vulnerability Mapping (Gaza Strip) | n/a | To highlight water vulnerable areas in the Gaza Strip | Data - freely accessible by WASH actors and EWASH ATF | TBD | Annual |  | IMO | TBD | GWC RAT (Tracy Wise) has determined framework, indicators & potential data sources | This needs to be turned into reality and linked to ActivityInfo (in collaboration with the CMWU / PWA) | With no comprehensive data very difficult to sell WASH
D. RESPONSE MONITORING
15 | Indicators and Standards for WASH |  | Establish indicators and standards for WASH response from e.g. WASH Strategy | Indicators and standards document | Take indicators highlighted in WASH Strategy and match existing data sources against it. | Annual one-off (SRP-linked) |  | IMOs | IMO | SRP indicators established |  | Try and link the relevant data collated here to the sitreps and other reporting requirements, as well as to a template
16 | Who Does What Where (3W) |  | To track humanitarian actors for coordination purposes in WASH sectors; to perform gap analysis | Registry of organisations in particular locations doing particular implementations | IMO collecting input from partners and updating the MASTER 3W. This is then forwarded to OCHA | Ongoing |  | IMOs | IMO | Gaza excel established | Activity Info should be proposed as an alternative to APIS - it has much greater flexibility to link with the other PWA databases | Harmonise the 3W so it feeds OCHA, Sitreps and other reporting requirements including defined SRP indicators.
E. REPORTING
17 | WASH Dashboard | A User Manual and worked examples on how to create both static and interactive dashboards -This is a KEY task for the IMO | To inform WASH Cluster partners and the wider response community of progress | PDF, interactive (Tableau) web dashboard |  |  |  |  | IMO | n/a | Ensure linkages with PHG / PWA for data, and EWASH ATF for presentation
18 | WASH Bulletin | A Briefing Sheet. Basic and advanced templates to create bulletins, including infographics tools | To inform WASH Cluster partners and the wider response community of progress. The Bulletin affords more space for narrative than the Dashboard and can include updates from partners to help in advocacy | PDF, interactive (Tableau) web dashboard |  |  |  |  | IMO | n/a | Ensure linkages with PHG / PWA for data, and EWASH ATF for presentation
19 | Gap Analysis | Excel template and example - This is a KEY task for the IMO | To show where there are gaps in interventions. | PDF, interactive (Tableau) web dashboard |  |  |  |  | IMO | n/a | Ensure linkages with PHG / PWA for data, and EWASH ATF for presentation
20 | SRP Biannual Updates | This is a KEY task for the IMO | To provide an overview of progress against the SRP plan of action & indicators | SRP report | Extract from Activity tracking / ActivityInfo | Bi-annual |  | IMO | IMO | n/a | Dependend on establishment of ActivityInfo
21 | SitReps OCHA | This is a KEY task for the IMO | To provide an overall assessment of the monthly situation, with both qualitative and quantitative data, for all Clusters | OCHA Sitrep | TBD | Monthly |  | IMO | IMO | Provided on monthly basis to OCHA | Continued provision of key updates / advocacy points to OCHA | Clarify inputs required each month
22 | SitReps UNICEF | n/a | To provide inputs as requested on the monthly situation | UNICEF Sitrep | TBD | Monthly |  | IMO | IMO | n/a | Cluster results should be integrated into UNICEF SitReps | Clarify inputs required each month
E. VISUALISATION & DISSEMINATION
23 | Website / Information Station | This is a KEY task for the IMO | To distribute relevant information | Maps, statistics, reports, data etc | Information to be available via email, website, and SitReps | Ongoing |  | IMO | IMO | Page established and managed on HR.info | Webpage needs to be built and hosted on PWA servers | Contact Majed (OCHA) to register as administrator of HR.info page
24 | Web Mapping | Web Mapping Manual and list of alternative tools for mapping WASH information online | To help partners to geographically visualise the needs and response | Web | Use the WASH step-by-step manual. The implementation of a Webmap will entail some previous knowledge of desktop GIS | Ongoing |  |  |  | n/a | Mashups of relevant audited data
F. PARTNER CAPACITY BUILDING TOOLS
25 | Training/ Upskilling | Tutorials and practical exercises in simple IM techniques -This is a KEY task for the IMO | Tools to build capacity of partners, incoming IMOs and Govt agency involved in WASH | Short course/one to one teaching | Short training course. Amend to suit the situation on the ground. E.g. if few computers, then it will be more of a lecture than practical exercise. | Ongoing | n/a | IMO | IMO / partners | n/a | Review of IM needs, identification of existing capacities, traning and user-resources.

## 6-month Workplan
WASH Sector support | Comment | Lead | Support
Consolidation of the coordination cell |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Coordination
Recruitment of Transition Coordinator | EWASH / PWA should be involved | UNICEF | SAG; PWA
Recruitment of EWASH Coordinator | Cluster / PWA should be involved | TBD | UNICEF; PWA
Training of EWASH Coordinator | Global WASH Cluster could potentially support | UNICEF | GWC / TBD
Fundraising for coordination resources | EWASH/PWA/Cluster | All | All
Information Management
Recruitement of oPT IMO | EWASH / PWA should be involved | UNICEF | SAG; PWA
Training of oPt IMO | Global WASH Cluster could potentially support | UNICEF | GWC / TBD
Mapping of partners with IM capacities | Possible simultaneous audit of datasets - in coordination with EWASH ATF | TBD | UNICEF
Fundraising for information management resources | Once clear what is needed for the sector | All | All
Consolidation of operational architecture
West Bank
Formalisation of Strategic Advisory Group | EWASH Steering Committee. Ideally provides an accepted sustinable governance structure to provide direction to any sectoral coordinator | UNICEF | SAG; PWA
Elaboration of ToRs | Should include oversight of the coordination function (validation of workplan, monthly reporting following meetings, etc.) | WSC / SAG | bar: 1 to 2
Validation of ToRs |  | Partners | bar: 3 to 4
Creation of Technical Working Groups |  | SAG
WASH Monitoring WG | Need to ensure a harmonised structure; easy access; comprehensive coverage; financial / technically sustainable setup | PHG | GVC; ACF; UNICEF
Elaborate ToRs / scope | What is the group aiming to produce (within 6 months)? Who is going to do What by When? Reports on progress in each monthly meeting | WSC / SAG / WG members | bar: 4 to 5
Harmonise indicators / method |  | WG | bar: 6 to 8
Ensure potential linkage to PWA systems |  | WG | bar: 7 to 9
Consolidate / collect data |  | WG | bar: 10 to 26
Water Scarcity WG | Need to ensure a finalised Water Scarcity Framework | GVC | UNICEF; PWA
Elaboration of ToRs / scope | What is the group aiming to produce (within 6 months)? Who is going to do What by When? Reports on progress in each monthly meeting | WSC / SAG / WG members | bar: 6 to 7
Discussion with donors to understand concerns / interests | To understand current concerns / interests - to be picked up more comprehensively in | WG
Lessons Learnt / constructive evaluation from Governance pilot |  | WG
Demolitions WG |  | Consortium | UNICEF; PWA
Lessons Learnt |  | WG
Best Practices |  | WG
Gaza Strip
Formalisation of Strategic Advisory Group | Should focus on supporting the CMWU / PWA; providing operational coordination / basic IM support in the Governorates; and providing direction to the cluster workplan | UNICEF | SAG; PWA
Elaboration of ToRs |  | WSCC / SAG | bar: 1 to 2
Validation of ToRs |  | Partners | bar: 3 to 4
Creation of Technical Working Groups |  | SAG
WASH Monitoring WG | Mapping out of flood risk areas; unserved areas; underserved areas - if not the PHG monitoring (adapted to context) | NRC/PHG? | TBD
Elaborate ToRs / scope | What is the group aiming to produce (within 6 months)? Who is going to do What by When? Reports on progress in each monthly meeting | WSCC / SAG / WG members | bar: 5 to 6
Water Trucking / Quality WG | Moving towards regulation of the private sector actors | ACF | TBD
Elaborate ToRs / scope | What is the group aiming to produce (within 6 months)? Who is going to do What by When? Reports on progress in each monthly meeting | WSCC / SAG / WG members | bar: 5 to 6
TBD | Onsite sanitation; hygiene promotion; hygiene kits; household water treatement; flooding | TBD | TBD
Elaborate ToRs / scope | What is the group aiming to produce (within 6 months)? Who is going to do What by When? Reports on progress in each monthly meeting | WSCC / SAG / WG members
oPt
Creation of a Strategic Operating Framework | Iterative document: Outlines structure, how we work, links between GS & WB (e.g. data flows), any standards and indicators, etc. Should outline plans to move to integrate into the WSDWG and should be updated with Strategies as they're developed | SAG
Drafting of the SOF |  | WSC / SAG | bar: 5 to 8
Revision and validation by cluster members |  | Partners | bar: 9 to 10
Finalisation of the SOF |  | WSC / SAG | bar: 11 to 12
Final validation by cluster members |  | Partners | bar: 13 to 14
Information Management
Creation of website |  | TBD | SAG
Consultation with key stakeholders | PWA, SAG, Donors, OCHA, EWASH ATF | IMO / WSC | bar: 1 to 4
Conceptual design / scope of content |  | IMO | bar: 5 to 6
Validation of concept by SAG |  | SAG | bar: 6 to 7
Development of site |  | IMO | bar: 8 to 9
Population of site |  | IMO / Partners | bar: 10
Maintenance of the site | Simple updates - long term capacity | TBD | bar: 11 to 26
Mailing Lists | Switch over to mailchip for mailing list management | UNICEF | EWASH ATF; PWA
Insert a widget for sign up/out on website | Need to discuss value of using same MailChimp account between actors (EWASH/ ATF/ PWA) | IMO / WSC | bar: 1 to 4
Development of IM system (stand-alone) |  | TBD | SAG
Review of APIS data and workshop results | To identify system requirements (e.g. reporting requirements; user-interests; etc) | IMO | bar: 1 to 4
Consultation with key stakeholders |  | IMO / WSC | bar: 1 to 4
Proposal of conceptual structure |  | IMO | bar: 5
Review of options | Useful to consult with OCHA IMU; GWC; UNICEF RO | IMO / WSC | bar: 6 to 7
Validation of concept / option by SAG |  | SAG | bar: 8 to 9
Development of system |  | IMO | bar: 10 to 11
Develop training and user-manual | Both for usage, and for setting up own agency's and setting up API to directly feed the overall one | IMO | bar: 12
Training & remote support | Both for usage, and for setting up own agency's and setting up API to directly feed the overall one | IMO / partners | bar: 13; 16; 20; 24
Development of IM system (integrated)
Mashup with other key datasets
Incorporation of other key sectors activity info / indicators?
IM Capacity Building |  | UNICEF | TBD
Consultation on IM needs |  | IMO | bar: 1 to 4
Identification of existing expertises |  | IMO | bar: 1 to 4
Development of training and support materials |  | IMO / Partners | bar: 14 to 15; 18; 22
Training |  | IMO / Partners | bar: 15; 19; 23
KAP surveys
ODK / KOBOCAD
ActivityInfo
Operationalisation of the Sector
Monitoring & Reporting | See IM Strategy | UNICEF | SAG
Design & validate dashboard |  | IMO | bar: 8
Design & validate bulletin |  | IMO | bar: 7
Design & validate gap analysis |  | IMO | bar: 8
Ensure monthly update of Activity Tracking |  | IMO | bar: 16; 20; 24
Ensure quarterly inputs to SRP monitoring |  | IMO | bar: 11 to 12; 23 to 24
Strategy development | To be integrated and updated in the Strategic Operating Framework | TBD | SAG
Linkages to Development Sector | Goal to integrate as a sub-set of the Water Development group. How to link / feed into strategies / priorities? | TBD | SAG
Linkages to Academic / Research Sector | How to better link / use the research sector on: - technical issues - advocacy issues - quality & learning - technical resources & training | TBD | SAG
Advocacy | Operational through ICCG/AWG/HCT Policy through EWASH ATF | TBD | SAG
Contingency Planning |  | TBD | SAG

## Drafts
Title | Document
SAG ToRs & Role
Coordinator ToRs
Co-Coordinator ToRs
IMO ToRs
Initial Strategic Operating Framework