## Workplan
Workplan
| EID HOLIDAY |  | JUNE | [29 empty] | JULY | [29 empty] | August | [30 empty] | September
| Global workshop |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Planning: Tool, coverage and scope | FOCAL POINT
| Finalisation of indicators and questionnaire | X | bar: JUNE 1; JUNE 4 to JUNE 8; JULY 2 to JULY 6; JULY 9
| Identification of partners | X | bar: JUNE 6 to JUNE 9; JUNE 11; JULY 2 to JULY 6; JULY 9
| Finalisation of coverage | X | bar: JUNE 11 to JUNE 15; JULY 2 to JULY 6; JULY 9
Documentation and assessment planning | bar: JUNE 1 to August 31
| Write up of ToR | X | bar: JUNE 4 to JUNE 8; JUNE 11 to JUNE 13; JULY 2 to JULY 6; JULY 9
| Feedback incorporation for ToR | X | bar: JUNE 14 to JUNE 15; JUNE 18; JULY 2 to JULY 6; JULY 9
| Kobo development and testing | X | bar: JUNE 12 to JUNE 14; JULY 2 to JULY 6; JULY 9
| Sampling and daily targets for coverage finalised | X | bar: JUNE 12 to JUNE 13; JULY 2 to JULY 6; JULY 9
| Training materials finalised | X | bar: JUNE 13 to JUNE 15; JULY 2 to JULY 6; JULY 9
| Data checking system and guidelines established | X | bar: JUNE 18 to JUNE 20; JULY 2 to JULY 6; JULY 9
Data collection and FLATs | bar: JUNE 1 to August 31
| Selection and hiring of numerators | X | bar: JUNE 13 to JUNE 15; JUNE 18 to JUNE 22; JULY 2 to JULY 6; JULY 9
| Setting up training and data checking plan | X | bar: JUNE 18 to JUNE 22; JULY 2 to JULY 6; JULY 9
| Piloting and training in all hubs | X | bar: JUNE 20 to JUNE 22; JUNE 25 to JUNE 29; JULY 2 to JULY 6; JULY 9
| Data collection kick off | X | bar: JUNE 25 to JUNE 29; JULY 2 to JULY 6; JULY 9 to JULY 13; JULY 16 to JULY 20; JULY 23 to JULY 27; JULY 30 to August 3
| Ongoing data checking / cleaning | X | bar: JUNE 25 to JUNE 29; JULY 2 to JULY 6; JULY 9 to JULY 13; JULY 16 to JULY 20; JULY 23 to JULY 27; JULY 30 to August 3
Data cleaning, preliminary analysis and drafting | bar: JUNE 1 to August 31
| Finalizing data cleaning with final follow-ups | X | bar: JULY 2 to JULY 6; JULY 9; August 6 to August 10
| Validating and delivering dataset for HNO | X | bar: JULY 2 to JULY 6; JULY 9; August 13 to August 15
| Develop analysis plan and submit for review | X | bar: JULY 2 to JULY 6; JULY 9; August 13 to August 15
| Develop draft report structure based on analysis plan | X | bar: JULY 2 to JULY 6; JULY 9; August 13 to August 15
| Report draft structure shared with cluster and feedback incorporated | X | bar: JULY 2 to JULY 6; JULY 9 to JULY 13
| Preliminary findings presentation to be drafted, reviewed and delivered | X | bar: JULY 2 to JULY 6; JULY 9; August 16 to August 17; August 20 to August 24; August 27 to August 31
| Drafting and finalising factsheets | X | bar: JULY 2 to JULY 6; JULY 9; August 22 to August 24; August 27 to August 31
| Drafting and finalising report | X | bar: JULY 2 to JULY 6; JULY 9; August 22 to August 24; August 27 to August 31; September 3 to September 7; September 10 to September 14
| Review and feedback incorporation internal | X | bar: JULY 2 to JULY 6; JULY 9; September 13 to September 14; September 17 to September 21
| Review and feedback incorporation exteral | X | bar: JULY 2 to JULY 6; JULY 9; September 24 to September 28
| Submission to cluster | X | bar: JULY 2 to JULY 6; JULY 9; September 28