| **Outcome** | **Output** | **Indicators** | **Baseline**  **July ‘17** | **Target June 18** | **Target**  **June ‘19** |
| --- | --- | --- | --- | --- | --- |
|  | | | | | |
| **Strategic Objective 1: Functional coordination mechanism in humanitarian WASH response** | | | | | |
| 1.1 Stronger WASH cluster active and GWCs 6+1 core functions are achieved | 1.1.1 Humanitarian WASH agencies are in cluster approach  1.1.2 Minimum Requirement of GWCs 6+1 core functions are operational | - List of humanitarian wash agencies in cluster  - Global WASH Cluster’s yearly evaluation report | -- % | 73% | 85% |
| 1.2 Cluster coordination functional and productive | 1.2.1 Regular cluster meeting  1.2.2 Regular SAG and TWiG meeting | - Meeting minutes  - Strategic and technical documents, ToRs  - Plan of action  - Forms, formats, templates, checklists | -- % | 73% | 85% |
| 1.3 Stronger information management mechanism is functional | 1.3.1 Documentation of humanitarian WASH response data, information and analytical reports | - 4W, maps, reports etc. | --% | 73% | 85% |
| 1.4 Active and strong presence in inter cluster mechanism and HCTT | 1.4.1 linkage and networking with other cluster and HCTT | - inter cluster meeting minutes  - HCTT meeting minutes | 30% | 73% | 85% |
|  | | | | | |
| **Strategic Objective 2: Humanitarian WASH agencies are prepared to deliver quality WASH response** | | | | | |
| 2.1 Coordinated WASH response is activated within 72 hours of disaster | 2.1.1 Agreed and approved Emergency Response Preparedness Plan (ERPP), Contingency Plan | - ERPP  - Contingency plan | 0 | 1 | 1 |
| 2.2 WASH supply is available for first phase response | 2.2.1 Contingency stock / prepositioning of wash materials | - List of WASH materials available in different part of the country | 0 | 1 | 2 |
| 2.3 Deliver quality Humanitarian WASH response | 1.3.1 Mapping capacity to respond  1.3.2 Better capacity | - Capacity mapping report  - training/workshop report | 0 | 1 | 2 |
|  | | | | | |
| **Strategic Objective 3: Functional WASH coordination in district level (in disaster prone districts)** | | | | | |
| 3.1 Humanitarian WASH response is coordinated in district level | 3.1.1 District WASH cluster formed/reformed  3.1.2 Two-way information flow (national-district) | - Updated list of district clusters  - Documents, 4W | 0 | 5 | 10 |
| 3.2 District WASH cluster is functional | 3.2.1 Regular cluster meeting at district level | - Meeting minutes | 0 | 5 | 10 |
|  |  |  |  |  |  |
| **Strategic Objective 4**: Adhering common technical and programme quality standards | | | | | |
|  |  |  |  |  |  |
| 4.1 Humanitarian WASH agencies adhering common technical standard and guidelines | 4.1.1 WASH agencies delivering common and technically standard WASH services | - Operational Guidelines for WASH in Emergencies, Bangladesh | 0 | 1 | 1 |
| 4.2 Relevant policies, guidelines, technical standards, etc are followed | 4.2.1 WASH partners have better understanding of policies, strategies of Bangladesh Government and international policies/strategies/standards e.g. Sphere, climate change, gender, disable people, elderly people | - Training/workshop report  - stories/case studies from partners | 0 | 1 | 2 |
| 4.3 Common and standard hygiene materials and messages ensured | 4.3.1 Guidance for hygiene kits are followed  4.3.2 Contents reviewed and key hygiene messages are agreed and disseminated | - Agreed list of materials for hygiene kit  - agreed and common hygiene messages  - IEC materials | 0 | 1 | 2 |
|  |  |  |  |  |  |
| **Strategic Objective 5: Effective monitoring mechanism is functional in humanitarian WASH response** | | | | | |
| 5.1 Appropriate Monitoring system are in place | 5.1.1 Affected community, stakeholders and independent sector are involved in monitoring | - Monitoring Strategy  - List of agreed indicators | 0 | 1 | 1 |
|  |  |  |  |  |  |
| **Strategic Objective 6: Adhering cross cutting issues in humanitarian WASH response** | | | | | |
| 6.1 Ensured equitable wash services to vulnerable people (women, girls, children, disable and elderly people) | 6.1.1 Women, adolescent girls, children, elderly people, people with disability received equitable humanitarian WASH assistance | - Guideline, reports | 0 | 1 | 1 |
| 6.2 Climate change issues ensured in Humanitarian WASH response | 6.2.1 Humanitarian WASH response guideline for comprising climate change | - guideline, reports | 0 | 1 | 1 |